## Sheet1 Performance Metrics Temp
Performance Metrics & Analysis
Metric | Current | Benchmark | Gap Analysis | Recommendations | Responsibility | Deadline | Status
(e.g., Total Procurement Cost) | (Value) | (Target) | (Analysis) | (Strategy) | (Responsible for the task) | (Time frame) | (Progress)
SAMPLE FILLED IN TEMPLATE
Metric | Current Performance | Benchmark/Target | Gap Analysis | Recommendations | Responsibility | Deadline | Status
Total Procurement Cost | $450,000 (FY 2023) | $400,000 (FY 2024 Target) | $50,000 over target | Renegotiate contracts with key suppliers for better pricing and terms. | Procurement Manager | Q2 2024 | In Progress
Supplier On-time Delivery Rate | 85% | 95% | 10% below target | Implement performance-based incentives for suppliers. Encourage suppliers to improve delivery times. | Supplier Relations Manager | Q3 2024 | Not Started
Purchase Order Cycle Time | 15 days | 10 days | 5 days longer than the target | Automate purchase order processing using procurement software to reduce cycle time. | Process Improvement Team | Q3 2024 | Not Started
Rate of Returns or Complaints | 5% | 2% | 3% higher than target | Enhance quality control measures and perform regular audits on supplier deliveries. | Quality Assurance Manager | Q4 2024 | In Progress
e-Procurement Tool Adoption | Partially adopted | Full adoption | Not fully adopted | Invest in full e-procurement system integration. Provide staff training on new tools. | IT Department | Q1 2025 | Not Started
Sustainable Purchase Ratio | 40% | 60% | 20% below target | Source more from certified sustainable suppliers. Educate procurement staff on sustainability criteria. | Sustainability Coordinator | Q4 2024 | In Progress

## Sheet2 Procurement Management
Procurement Management Table
Date：
Date： | Reserve | [5 empty] | Actual
| Purchase unit | Item | Quantity | Unit price | subscription date | Procurement Service (Reservation) | Summons number | Procurement Service (Decision) | Quantity | Unit price | Amount | Delivery time | Inspection results | Paid | Notes
SAMPLE FILLED IN TEMPLATE
Date： | Reserve | [5 empty] | Actual
| Purchase unit | Item | Quantity | Unit price | subscription date | Procurement Service (Reservation) | Summons number | Procurement Service (Decision) | Quantity | Unit price | Amount | Delivery time | Inspection results | Paid | Notes
2024-04-10 | IT Department | Laptop | 10 | $1,200 | 2024-04-15 | Approved | IT-1234 | Completed | 10 | $1,200 | $12,000 | 2024-05-01 | Passed | Yes | Delivered on time
2024-04-15 | HR Department | Office Chairs | 20 | $150 | 2024-04-20 | Pending | HR-5678 | Awaiting Approval | 20 | $150 | $3,000 | 2024-06-01 | Pending | No | Urgent requirement
2024-04-20 | Marketing | Promotional Banners | 50 | $25 | 2024-04-22 | Approved | MK-9101 | Completed | 50 | $25 | $1,250 | 2024-04-30 | Passed | Yes | For upcoming marketing event